Working package “Cabling and feedthroughs”

|  |  |  |
| --- | --- | --- |
| Subtask | Time period | Comments |
| 1. Decision about the detector flanges
 | Mid of February | All |
| 1. Design of the DSSD and HV flanges
 | End of February | Michel, Oleg |
| 1. Purchasing the flanges, feedthroughs and connectors
 | Beginning of March | Michel |
| 1. Design of DSSD cables with/without capacitors
 | End of March | Gerhard May |
| 1. Construction of DSSD cables without capacitors
 | End of March | Oleg, Manfred, Brano |
| 1. Construction of DSSD cables with capacitors
 | After a positive test of ASIC board | Gerhard May |
| 1. Design of DSSD air-side cables
 | April | Oleg, Manfred, Brano |
| 1. Construction of DSSD air-side cables
 | End of April | Oleg, Manfred, Brano |
| 1. Design and construction of cables for the thermosensors
 | Middle of March | Oleg |
| 1. Design and construction of cables for the SiLis
 | End of March | Brano, Manfred |
| 1. Grounding and shielding scheme for SiLis + DSSDs
 | Middle of March | Oleg |
| 1. HV cables for DSSD and SiLis
 | End of March | Oleg, Brano, Manfred |
| 1. Design of the interfaces, cables + connectors for the pumps, valves, vacuum sensors
 | End of February (after a design of vacuum system is fixed) | Oleg |
|  |  |  |

Personnel: Oleg, Manfred, Brano, Michel, G. May, P. Schakel, Mirko